## ProjectPlan
Working Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Start of the week | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05
|  |  | 2/12 Kick - off | 9/12 Discussion on Brain | 16/12 Discussion on Embedded 18/12 receive car kit 19/12 Discussion on Computer
Sensing and input working package | 2024-11-18: Documentation on the given guides and projects. Chose main languages and technologies Create/adapt project plan Members tasks asignation; 2024-11-25: Ubuntu 20.04 & Ros Noetic Study and document vehicle architecture Create/adapt project plan Study given start-up code; 2024-12-09: Team photo submission Research ROS, sensors, and initial tools Study and document vehicle architecture Plan GitHub repository structure Create/adapt project plan Study given start-up code; 2024-12-16: Camera handling, preprocessing, noise cancelling, ROIs definition; 2025-02-03: Define other necessary sensors, define use-case, integration (IMU, distance), preprocessing, noise cancelling.; 2025-05-05: BFMC
Define use-case and test given servers information (localisation on map, cars interaction, gps interaction)
[18 empty] | Induce noise on all sensors and systems |  |  |  | Other functionalities and optimizations
Perception and scene understanding working package | 2024-12-16: Lane detection; 2025-01-06: Intersection detection; 2025-01-27: Traffic sign detection; 2025-02-17: Traffic light detection
[12 empty] | Position fusion | [5 empty] | Traffic lights detection & classification
[14 empty] | Define objects properties file |  |  |  | Object detection & classification
Environmental server interaction
Other functionalities and optimizations
Behaviour and motion plan working package | 2024-12-16: Define project architecture and communication between packages; 2025-01-20: Define path planning and validation; 2025-02-17: Define robustness and safety measures
Define decision making --> priorities of actions and state flow
[18 empty] | Induce noise on systems to valdiate robustness (loss of image, burned image, road search, undefined objects and states) |  |  |  | Other functionalities and optimizations
Vehicle control working packages | 2024-12-16: Lane following and speed control; 2025-01-20: Intersection navigation; 2025-02-17: Simple action taking maneuvers (parking, stop for traffic sign, stop for traffic light, stop for pedestrian); 2025-03-17: Complex action taking maneuvers (swith lane for static and mobile car, road search)
Other functionalities and optimizations
Final result & Demo | 2024-11-18: Team can control the physical car remotely and the virtual car on the simulator.; 2024-12-16: Car can keep a lane, can make a curve; 2025-01-20: Car can navigate in intersection; 2025-02-17: Car can go on a pre-determined path, stop at stop sign, park at parking sign, slow at crosswalk; 2025-03-17: While detecting and calculating it's position, the Car can dynamicaly go to specified checkpoint, react to traffic lights, interact with other cars and send environemt data)
|  |  |  | Team defines and creates it's own physical testing environment |  |  |  | Team defines a way of parallel developing and testing
Team installs the virtual testing environment
Other functionalities and optimizations
Deadlines | 2024-12-09: 2024-12-16; 2025-01-13: 2025-01-20; 2025-02-10: 2025-02-17; 2025-03-10: 2025-03-17; 2025-04-14: 2025-04-21; 2025-05-05: 2025-05-21
Checkpoint | 2024-12-09: 1st report; 2025-01-13: 2nd report; 2025-01-27: Lunar new year; 2025-02-10: 3rd report; 2025-03-10: Mid-term quality gate; 2025-04-14: 4th report; 2025-05-05: 5th report
Requirements | 2024-12-09: The team should at least control the car with the given start-up code.; 2025-01-13: The team should at least link the input data to a rough output (for example, camera to motors).; 2025-02-10: The team should have at least shown some in-depth algorithmic approaches (for example, show a pretty solid lane-keeping); 2025-03-10: The team should have at least some autonomous features ready (for example, show the car keeping its lane and reacting to some signs or obstacles); 2025-04-14: The team should show autonomous features almost complete (for example, show specific reactions to particular cases: fog, roundabout).; 2025-05-05: Team should show autonomous features complete (car can react to any obstacle on the map).
https://bosch-future-mobility-challenge-competition-regulation.readthedocs-hosted.com/data/projectdevelopment.html